## Executive Dashboard (hidden)
MGFA Scientific Session Command Center
Executive dashboard for abstract review, program build, presenter operations, logistics, risk, and onsite readiness.
Total PM Tasks |  | Complete |  | In Progress |  | Blocked |  | Red Items |  | Milestones
1 |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
Operational Readiness |  |  | Key Milestones | [5 empty] | RAG Mix
Review Completion | 0% |  | Milestone | Due | Owner | Status | RAG |  | Green | #REF!
Program Readiness | 0% |  | Reviewer scores due | 2026-05-20 | Reviewers / MJ | In Progress | Red |  | Amber | #REF!
Presenter Readiness | 0% |  | AANEM Excel report | 2026-05-25 | AANEM / Julie | Not Started | Amber |  | Red | #REF!
Poster Readiness | 0% |  | Abstract decisions + edited abstracts to AANEM | 2026-06-15 | MJ | Not Started | Red
Logistics Readiness | 0% |  | Final program to Tracy/AANEM | 2026-07-01 | MJ | Not Started | Red
|  |  | Poster logistics packet | 2026-07-15 | MJ | Not Started | Green
|  |  | Onsite space preview | 2026-09-28 | MJ / Tracy / AVFX | Not Started | Green
Executive Watchlist |  |  | Scientific Session + Poster Session | 2026-09-29 | MJ / MGFA | Not Started | Green
• Reviewer closeout is the immediate critical path.
• Author change requests must be audited before June 15; AANEM may need manual updates.
• All official presenter communications should come from MGFA.
• Oral presenters should also have posters as a backup.
• Poster install opens Monday Sept 28 after 6 PM; removal required Tuesday Sept 29 by 4 PM to avoid fees.

## MGFA 2026 Session Program
Event Name: Myasthenia Gravis Foundation of America (MGFA) Scientific Session at AANEM 2026
MGFA Oral Presentations: Tuesday, September 29, 2026: 8:00am - 2:30pm EDT
MGFA Poster Session: Tuesday, September 29, 2026: 7:30am - 3:30pm; Presenters at posters: 2:30pm - 3:30pm EDT
Start Time | End Time | Title | Speaker
WELCOME AND KEYNOTE ADDRESS
8:00 | 8:05 | Welcome Remarks | Samantha Masterson, MGFA President and CEO
8:05 | 8:10 | Introduction of Keynote Speaker | Kelly G. Gwathmey, MD
8:10 | 8:45 | Keynote Address | Sarah Hoffmann, MD, MSc
8:45 | 8:54 | Q&A | Moderator: Kelly G. Gwathmey, MD
SESSION A
Biomarkers, Basic Science, and Diagnostics
8:54 | 8:55 | Introduction | Richard J. Nowak, MD, MS
8:55 | 9:03 | Average Volume-Assured Pressure Support (AVAPS) in Monitoring Respiratory Muscle Weakness in Myasthenia Gravis | Elizabeth Madole and Alex Fay, MD, PhD
9:03 | 9:10 | Revisiting the Neuromuscular Junction in Acetylcholine Receptor Antibody-Positive Myasthenia Gravis: A Multimodal Study of Human Endplate Pathology | Sarah Hoffmann, MD, MSc
9:10 | 9:17 | iPSC-derived Neuromuscular Junction Organoids Recapitulate Presynaptic Dysfunction in Lambert-Eaton Myasthenic Syndrome | Caleb Aguayo, PhD Candidate
9:17 | 9:24 | Complement C5 Inhibition Preserves the Neuromuscular Junction in Myasthenia Gravis: An Integrated Morphology and In Vivo Nerve-Evoked Muscle Function Biomarker Platform in Rodent Models | Chris Ward, PhD
9:24 | 9:30 | Q&A | Moderator: Richard J. Nowak, MD, MS
9:30 | 10:00 | Coffee Break
SESSION B
Therapeutics and Clinical Trials
10:00 | 10:01 | Introduction | Tuan Vu, MD and Neelam Goyal, MD
10:01 | 10:08 | Psychometric Evaluation of the Myasthenia Gravis Impairment Index Patient Reported Outcome Ocular Score in Ocular Myasthenia Gravis: Results From a Phase 3 Clinical Trial in Ocular Myasthenia Gravis | Jeff Guptill, MD, MHS, MA
10:08 | 10:15 | Efficacy and Safety of Efgartigimod in Participants With Generalized Myasthenia Gravis Who Lack Detectable Anti-Acetylcholine Receptor Antibodies: One-Year Results of ADAPT SERON | James F. Howard, Jr., MD, FAAN
10:15 | 10:22 | Primary Analysis of Phase 2 of KYSA-6, an Open-Label, Single-Arm, Multicenter Study of Miv-cel (KYV-101), a Fully Human CD19 Chimeric Antigen Receptor T-Cell Therapy in Generalized Myasthenia Gravis | Srikanth Muppidi, MD
10:22 | 10:29 | Comparison of Cemdisiran vs Placebo on Hospitalization Rate in the Phase 3 Double-Blind NIMBLE Trial | Ali Habib, MD
10:29 | 10:36 | Telitacicept for Generalized Myasthenia Gravis: Depth of Response Across 48 Weeks in a Phase 3 Study Conducted in China | Richard J. Nowak, MD, MS
10:36 | 10:43 | Slow Channel Congenital Myasthenic Syndrome: Treatment Outcomes and Cohort Insights | Eduardo Estephan, MD, PhD
10:43 | 10:50 | Durability of Response Following Retreatment with Descartes-08, an Autologous BCMA-Directed mRNA CAR-T Cell Therapy, in Generalized Myasthenia Gravis: 12-Month Follow-Up | James F. Howard, Jr., MD, FAAN
10:50 | 10:57 | RESET-MG: Clinical Trial Evaluating Rese-cel (Resecabtagene Autoleucel), a Fully Human, Autologous 4-1BB CD19-CAR T Cell Therapy in Generalized Myasthenia Gravis | Ali Habib, MD
10:57 | 11:04 | Clinical Deterioration, Rescue Therapy, and Hospitalization Among Patients with Generalized Myasthenia Gravis (gMG): Results From the PREVAIL Trial of Gefurulimab | James Winkley, MD
11:04 | 11:11 | FCGR3A Polymorphisms and Treatment Timing in Rituximab Response in MuSK-MG | Jonathan Morena, DO
11:11 | 11:30 | Q&A | Moderators: Tuan Vu, MD and Neelam Goyal, MD
11:30 | 13:00 | Lunch Break Not Served at MGFA Scientific Session – On Your Own
SESSION C
Seronegative MG and Congenital Myasthenic Syndromes
13:00 | 13:01 | Introduction | Gianvito Masi, MD
13:01 | 13:08 | Adeno-Associated Virus-Mediated Gene Therapy of Synaptotagmin 2-Deficient Mice | Olivia Morgans, DVM Candidate
13:08 | 13:15 | Determining Autoimmunity in Seronegative Myasthenic Syndromes: Insights From Live-CBA Testing and a Human Muscle Cell Assay in a Large Central European Cohort | Sarah Hoffmann, MD, MSc
13:15 | 13:20 | Q&A | Moderator: Gianvito Masi, MD
Patient Care, Outcomes, Digital Health & Real-World Evidence
13:20 | 13:21 | Introduction | Ali Habib, MD
13:21 | 13:28 | Interpreting Clinically Meaningful Improvement on the Myasthenia Gravis Impairment Index (MGII) Patient Reported Outcome (PRO) Ocular Score: Responder Analyses From a Phase 3 Clinical Trial in Ocular MG | Jeff Guptill, MD, MHS, MA
13:28 | 13:35 | Validation of Myasthenia Gravis Outcome Measure Thresholds in a Real-World Clinical Practice Cohort: A Retrospective Duke MG Registry Study | Karandeep Singh Bhatti, MBBS
13:35 | 13:42 | Integrated Group-Based and Machine Learning Analysis Reveals Sex-Related Clinical Signatures in Autoimmune Myasthenia Gravis | Paolo Doksani, MD
13:42 | 13:49 | AI-Based Ocular Motor Digital Biomarkers for Precision Detection of Ocular Myasthenia Gravis | Kemar E. Green, DO, FANA
13:49 | 13:56 | ME&MG™ Digital Biomarkers Scores Reflect MGFA Severity Classification | Bhaskar Dutta, PhD
13:56 | 14:03 | Placebo-Arm Response in Generalized Myasthenia Gravis Clinical Trials: A Systematic Review and Meta-Analysis | Hazem Iaali, MD
14:03 | 14:15 | Q&A | Moderator: Ali Habib, MD
Closing Remarks
14:15 | 14:30 | Closing Remarks & Wrap-Up | Jenny McCue, Vice President, Research & Clinical Development, MGFA
MGFA Scientific Session - Poster Session | Floridian Ballroom D-I (Lobby Level )
14:30 | 15:30 | Converse with researchers about their published work. | Find poster numbers and read full abstracts: https://myasthenia.org/events/2026-scientific-session/

## RAID Register (hidden)
RAID Register
Risk, assumption, issue, and dependency management for proactive executive oversight.
RAID ID | Type | Risk / Issue / Assumption / Dependency | Impact | Likelihood | Priority | Owner | Mitigation / Action Plan | Trigger | Due Date | Status | RAG | Notes
R-001 | Risk | Reviewer scores incomplete by May 20 | High | Medium | High | MJ | Escalate same day; identify replacement/secondary coverage | Incomplete reviews at noon May 20 | 2026-05-20 | In Progress | Red
R-002 | Risk | Author edit requests missed before AANEM update | High | Medium | High | MJ | Maintain Author Change Log; submit manual update list to AANEM | Any author mismatch or request | 2026-06-10 | Not Started | Red
R-003 | Risk | Oral presenter misses presentation | Medium | Low | Medium | MJ | Require oral presenters to have poster backup | Presenter unconfirmed by deadline | 2026-06-24 | Not Started | Amber
R-004 | Risk | Posters not removed by 4 PM causing fees | Medium | Medium | High | MGFA Staff | Include removal language in all poster comms; onsite sweep | Posters still up at 3:45 PM | 2026-09-29 | Not Started | Amber
D-001 | Dependency | AANEM sends Excel scoring report May 25 | High | Medium | High | AANEM / Tracy | Follow up immediately if not received | Report not received by EOD May 25 | 2026-05-25 | Not Started | Amber

## Lessons Learned (hidden)
Lessons Learned / Retrospective
Post-event capture for 2027 process improvement and institutional memory.
Item ID | Category | Observation | Impact | Recommendation | Owner | 2027 Action? | Status | Notes
LL-001 |  | Need to expand Reviewer pool | High volume of assigned abstracts with various COIs making assignments difficult to delegate |  |  | TBD | Not Started
LL-002 |  | AANEM system shows all abstracts instead of assigned abstracts | Reviewer confusion and overscoring on unassigned abstracts |  |  | TBD | Not Started
LL-003 |  | AANEM system should allow flags for oral presentation |  |  |  | TBD | Not Started
LL-004 | [5 empty] | TBD | Not Started
LL-005 | [5 empty] | TBD | Not Started
LL-006 | [5 empty] | TBD | Not Started
LL-007 | [5 empty] | TBD | Not Started
LL-008 | [5 empty] | TBD | Not Started
LL-009 | [5 empty] | TBD | Not Started
LL-010 | [5 empty] | TBD | Not Started
LL-011 | [5 empty] | TBD | Not Started
LL-012 | [5 empty] | TBD | Not Started
LL-013 | [5 empty] | TBD | Not Started
LL-014 | [5 empty] | TBD | Not Started
LL-015 | [5 empty] | TBD | Not Started
LL-016 | [5 empty] | TBD | Not Started
LL-017 | [5 empty] | TBD | Not Started
LL-018 | [5 empty] | TBD | Not Started
LL-019 | [5 empty] | TBD | Not Started
LL-020 | [5 empty] | TBD | Not Started
LL-021 | [5 empty] | TBD | Not Started
LL-022 | [5 empty] | TBD | Not Started
LL-023 | [5 empty] | TBD | Not Started
LL-024 | [5 empty] | TBD | Not Started
LL-025 | [5 empty] | TBD | Not Started
LL-026 | [5 empty] | TBD | Not Started
LL-027 | [5 empty] | TBD | Not Started
LL-028 | [5 empty] | TBD | Not Started
LL-029 | [5 empty] | TBD | Not Started
LL-030 | [5 empty] | TBD | Not Started